## Action Plan Example
Public Health Center: |  |  | Publichealthville
Selected Strategy: | Engagement
Selected Goal& Objective: | Goal 7.1: increase outreach for PHN-delivered safety net services and collaborative activities to serve populations experiencing vulnerability around the priority program areas. Identify and plan strategies to improve health outcomes among populations in communities served by PHNs who experience: barriers to health services; health related social needs; significant life transitions.
Priority Program Areas: Reduce Vaccine Preventable Diseases; Improve the Health of Children; Prevent and Respond to Tuberculosis and other Infectious Diseases; Reduce Sexually Transmitted Infections; support community mental health and wellbeing
Lead: | Jane Doe
SMART Goal | We aim to provide 10 off-site clinical service clinics focused on STI and reproductive health services for at transitional and shelter housing paired with an educational session by 6/30/2025.
Result: [At the end of the goal due date, note your progress here.]
Action Steps (What &How) | Person Responsible | Due by when: | Metric (How will we know when it's achieved?) | Status
Develop list of potential transitional housing venues | George Orwell | 2024-08-30 | done/not done | Done 8/26
Outreach managers of those venues to explain services. (May need to break this out into individual housing unit manager and staff if there is a lot.) | William Shakes | 2024-09-10 | # of housing managers accepting | 4 of 6 managers accepted; 1 said no, 1 waiting for call back
Develop a survey for patrons on what educational topics they may be interested in. | Benny Hanna | 2024-09-10 | done/not done
Schedule clinics and presentations | Jack B. Nimble | ongoing
Build off-site clinic "go bin" | Danielle Steel | 2024-09-15 | done/not done
Session 1-September: "flu vaccination and you" at DV shelter; offer STI screening | Theodor Seuss | 2024-09-30 | # of inidividuals screened; # individulas attending presentation
Work on presentation content and activities | Theodor Seuss | 2024-09-30 | done/not done
pull together STI visit supplies and paperwork | Theodor Seuss | 2024-09-30 | done/not done
Session 2-October: "Your Baby's Development" at Family Shelter; offer family planning visits | Laura Wilder | 2024-10-31
November: TBD

## Action Plan Example (2)
Public Health Center: |  |  | Publichealthville
Selected Strategy: | Engagement
Selected Goal& Objective: | Goal 9.2 Develop section-wide programmatic activities to protect and promote individual and community mental health and enhance protective factors. Participate in local and statewide partnerships that are coordinating to advance community mental health and decrease substance misuse, suicide, IPV,and mental health crisis while working to enhance community protective factors.
Priority Program Areas: Reduce Vaccine Preventable Diseases; Improve the Health of Children; Prevent and Respond to Tuberculosis and other Infectious Diseases; Reduce Sexually Transmitted Infections; support community mental health and wellbeing
Lead: | Jane Doe
SMART Goal | We aim to initiate a local suicide prevention coalition.
Result: [At the end of the goal due date, note your progress here.]
Action Steps (What &How) | Person Responsible | Due by when: | Metric (How will we know when it's achieved?) | Status
Identify list of stakeholders | George Orwell | 2024-08-30 | done/not done | Done 8/26
Identify key data elements (YRBS, BRFFS, suicide rates in region/area.) | William Shakes | 2024-12-30 | # of housing managers accepting | 4 of 6 managers accepted; 1 said no, 1 waiting for call back
Connect with suicide prevention coalitions in other communities, and at Statewide level for resources | Benny Hanna | 2024-12-30 | done/not done
Discussions with other key community partners to help launch coalition | Little Richard | 8/30/24-12/30/24 | Data Hub (count of hours addressing)
Set up a meeting, inviting stakeholders to review data, propose coalition or other action. | Jack B. Nimble | 2025-01-30 | # of participants; outcome